RFI Module — Detailed Specification

1) Functional Modules

- Project Context & Setup

  - Create new project or import from:

    - Phase 3 (HR/Projects)

    - Phase 1 (Legal/Contracts)

  - If neither subscription is active → quick inline Create Project (minimum fields: Project Name, Client, Site, Contract Type, Contacts).

  - Contract selection (JBCC/NEC/FIDIC/GCC) drives time-bar rules.

- RFI Creation

  - Fields: Title, Discipline, Category, Description, Drawing/Detail Ref, Location/Chainage, Priority, Due-By.

  - Attachments: PDFs, images, CAD/DWG (or link to Document Control when Phase 13 is live).

  - Contract clause link (optional).

  - Auto RFI ID (e.g., RFI-000123-A).

- Routing & Notifications

  - Auto-assign by discipline/contact table.

  - Notify via email + in-app (optional WhatsApp status push later).

  - SLA timers start on Submitted.

- Response Workflow

  - Statuses: Draft → Submitted → Awaiting Response → Responded → Under Review → Closed.

  - Consultant reply via portal (or email bridge); attach revised sketches/drawings.

  - Versioning of responses and attachments.

- Time-Bar Automation

  - Contract-specific SLA rules (e.g., X working days).

  - Countdown, colour status, overdue flag + escalations.

  - Overdue / No Response → prompt: Create Notice in Phase 1 (pre-filled).

- Impact & Escalation

  - “Affects Time/Cost?” toggle on Responded/Review screens.

  - If Yes → button: Create Notification in Phase 1 (EOT/compensation, auto-filled with RFI context).

- Discussion Thread & Audit

  - Threaded comments, @mentions, inline file drops.

  - Immutable audit log: who/what/when (create, submit, respond, close).

- Registers & Dashboards

  - Master RFI Register (filters: project, discipline, status, overdue).

  - KPIs: total RFIs, open/closed, average response time, % overdue, by-discipline distribution.

  - Exports: PDF/Excel/CSV.

- AI Assistance (Phase 1+ features leveraged)

  - Auto classify discipline/priority from text.

  - Draft response suggestions from contract library + prior RFIs.

  - Detect potential time/cost impact cues.

  - Weekly summary auto-write for Phase 8 Reports.

- Reporting Integration (Phase 8)

  - Weekly/Monthly report widgets pull: counts, ageing, overdue, notable RFIs.

  - One-click “Add to Monthly Report”.

- Permissions & Roles

  - Contractor User: create/submit RFIs, view all RFIs on own project, initiate notices.

  - Consultant/Engineer: respond, upload marked-up drawings, request more info.

  - Client Rep: review/acknowledge, mark “Accepted/Instruction Issued”.

  - Legal Reviewer (Za-Eng): view overdue, create/approve notices/EOT.

  - Super Admin: global oversight, SLA rule templates.

- Configuration

  - SLA rule templates per contract type.

  - Discipline directory (Electrical, Civil, Structural, Architectural, etc.).

  - Outbound templates (email subjects, PDF headers).

  - Custom fields per client/project (optional).

2) Data Model (key entities)

- Project(id, name, client, contract_type, contacts[], status)

- RFI(id, project_id, title, discipline, description, priority, due_by, clause_ref?, location, status, created_by, created_at)

- RfiAttachment(id, rfi_id, type[file/link], file_ref, version, uploaded_by, ts)

- RfiResponse(id, rfi_id, responder_id, message, attachments[], responded_at)

- RfiThreadNote(id, rfi_id, author_id, text, files[], ts)

- SLAClock(rfi_id, start_ts, due_ts, paused?, stopped_ts, status)

- NoticeLink(rfi_id, notice_id, type[overdue|impact], created_ts)

- AuditLog(actor_id, entity, entity_id, action, before/after, ts)

3) Workflow (happy path)

- Create / Import Project → select Contract Type (drives SLA).

- New RFI → fill form + attach refs → Submit.

- Routing → assigned consultant notified, Awaiting Response starts timer.

- Response → attachments + message → Under Review.

- Review → mark Affects Time/Cost? (Yes/No).

  - If Overdue at any point → Create Notice (Phase 1).

  - If Impact = Yes → Create Notification (Phase 1).

- Close with resolution summary & links to revised docs.

- Data flows to Phase 8 weekly/monthly reports.

4) Scenario Walkthroughs

Scenario A: Contractor login → project import/creation → standard RFI → late response → notice

1. Login & Project Context

- Contractor logs in → RFI module home → “Select Project”.

- If project exists in Phase 3 (HR) or Phase 1 (Legal), choose from dropdown and import context (client contacts, contract type, time-bar rules).

- If not: click Create Project (minimal fields). Choose Contract Type (e.g., JBCC) to activate SLA rules.

2. Create RFI

- Click New RFI → enter Title “Clarify Beam Detail at Grid C-5”, Discipline “Structural”, Drawing Ref “S-A105”.

- Add photos of site rebar + snippet of drawing.

- System sets Due-By = +5 working days (from JBCC rule). Submit.

3. Routing & Tracking

- Assigned Structural Engineer auto-notified; RFI status = Awaiting Response.

- Dashboard shows countdown 5…4…3 days to due date.

4. Overdue Trigger

- No response by due date → RFI turns Overdue (red).

- System prompts button: “Create Notice in Phase 1 (Late/No Response)”.

- Contractor clicks → opens Phase 1 notice form pre-filled with:

  - Project, Contract Type, Clause reference (time-bar), RFI number, Dates.

- If contractor isn’t subscribed to Phase 1 → inline prompt:
“To generate contract notices and AI claims, please subscribe to the Legal Module.”

5. Close-Out

- Consultant later responds; Contractor reviews and closes RFI with resolution summary.

- Notice remains in Legal module for record and potential claim.

Scenario B: Missing drawings → RFI triggers time/cost impact → create impact notification/claim

1. RFI for Missing Drawing Info

- Contractor creates RFI: “Elevation Detail Missing for Classroom Facade”
Discipline: Architectural; Drawing Ref: “A-E210 (missing elevation detail)”.

2. Response with Change

- Consultant replies after 3 days with a new sketch requiring extra flashing and stainless fixings.

- Contractor reviews: this change adds time and cost.

3. Flag Impact & Create Notification

- On RFI screen, toggle “Affects Time/Cost? = Yes”.

- System shows “Create Notification → Phase 1” button.

- Click → Phase 1 notice opens pre-filled with:

  - RFI reference & response details

  - Description of additional works

  - Preliminary time impact (e.g., +5 days)

  - Cost impact placeholder (to be updated after QS review)

4. Link to ERP (Phase 5) later

- If ERP is active, the impact triggers a potential cost event for later valuation (subcontractor certificate/VO).

5. Reporting

- Weekly Report (Phase 8) auto-includes:

  - Highlight: “RFI-124 introduces additional flashing; notification issued; time impact 5 days (TBC).”

  - KPI updates: 1 new impact RFI this week.

5) Integration Points

- Phase 1 (Legal): Create Late/No Response Notices and Impact Notifications directly from RFI; pre-filled forms; back-links to RFI.

- Phase 3 (HR/Projects): Project selection/import; use project directory and contacts.

- Phase 5 (ERP): Optional hand-off for cost events (valuation/VO pipeline).

- Phase 8 (Reports): Auto-pull RFI summaries, overdue counts, and notable items into weekly/monthly reports.

- Phase 13 (Document Control, future): Deep drawing/version linking and side-by-side comparisons.

6) Security & Compliance

- Role-based access (tenant → project → role).

- AES-256 at rest, TLS 1.3 in transit.

- Immutable audit logs for legal defensibility.

- POPIA/GDPR compliant handling of files and personal data.

7) Acceptance Criteria (high level)

- RFIs cannot be created without a project context.

- Selecting a contract type auto-sets SLA time-bars.

- Overdue RFIs show notice-creation prompt and pre-fill Phase 1 forms.

- “Affects Time/Cost” toggling surfaces Phase 1 impact notice with RFI context.

- Registers export correctly (CSV/XLSX/PDF) and match on-screen filters.

- All actions leave a timestamped audit trail.